SERVICE CONTRACT NOTICE

Tourism promotion and development services

Lot 1 - Marketing and visibility services for tourism | Lot 2 - Tourism subject matter expert services
Republic of North Macedonia

# 1.	Reference

# RD-02-29-315-PP6-TD1

# 2.	Procedure

Simplified

# 3. 	Programme title

- INTERREG VI-A IPA Bulgaria – North Macedonia Programme 2021TC16IPCB006 (2021-2027)

# 4. 	Financing

Subsidy contract no: RD-02-29-315/02.04.2025

Project: “Low-carbon infinity trail” (Acronym: LIFT)

# 5. 	Contracting authority

Association Tourist Union Strumica - Strumica

CONTRACT SPECIFICATION

# 6. 	Nature of contract

Global price

PROJECT “LOW-CARBON INFINITY TRAIL-LIFT” REF. NO. BGMK0200039

# 7. 	Contract description

The contract covers tourism promotion and development services for the “Low-carbon infinity trail” (LIFT) project under the INTERREG VI-A IPA Bulgaria - North Macedonia Programme. Lot 1 includes production of 3 promotional videos, development of an integrated marketing strategy, establishment and management of social media channels, execution of a targeted social media campaign, content creation and media publications for the North Macedonian region, and production of marketing materials. Lot 2 involves expert services such as organizing focus groups and interviews, preparing a status report on low-carbon tourism readiness, developing an action plan, creating a multilingual digital “Diary of a Cyclist,” designing and piloting velo tour packages and developing a comprehensive cross-border tourism product “Infinity Trail.” All services aim to enhance sustainable tourism, visibility, and cross-border cooperation in the eligible regions.

# 8. 	Number and titles of lots

# This contract is divided into lots: yes

# Tenders may be submitted for: all lots

# Lot 1: Marketing and visibility services for tourism

# Lot 2: Tourism subject matter expert services

# 9. 	Maximum budget

Value excluding VAT (total): 31449.15 EUR

Value excluding VAT (Lot 1): 14542.37 EUR

Value excluding VAT (Lot 2): 16906.78 EUR

CONDITIONS OF PARTICIPATION

10.	Legal basis, eligibility and rules of origin

*****

The legal basis of this procedure is Regulation (EU) No 2021/1529 establishing the Instrument for Pre-accession Assistance (IPA III). See Annex a2a1 of the practical guide.

For this contract award procedure, participation is open to all natural persons who are nationals of and legal persons (participating either individually or in a grouping – consortium – of candidates/tenderers) which are effectively established in a Member State of the European Union or in an eligible country or territory as defined under Article 11 of Regulation (EU) No 2021/1529 establishing the Instrument for Pre-accession Assistance (IPA III).

Participation is also open to international and regional organisations.

# 11.	Number of tenders

No more than one tender can be submitted by a natural or legal person whatever the form of participation (as an individual legal entity or as leader or member of a consortium submitting a tender).  In the event that a natural or legal person submits more than one tender, all tenders in which that person has participated will be excluded.

No restrictions may be made in the number of lots a tenderer can be awarded.

The tenderer may submit a tender for one lot only, several lots or all of the lots, but only one tender per lot. Contracts will be awarded lot by lot and each lot will form a separate contract. If the tenderer is awarded more than one lot, a single contract may be concluded covering all those lots.

# 12.	Grounds for exclusion

As part of the tender, tenderers must submit a signed declaration, included in the tender form, to the effect that they are not in any of the exclusion situations listed in Section 2.4.2.1. of the practical guide. Where the tenderer intends to rely on capacity providing entities or subcontractor(s), he/she must provide the same declaration signed by this/these entity(ies).

Tenderer included in the lists of EU restrictive measures (see Section 2.4. of the PRAG) at the moment of the award decision cannot be awarded the contract.

# 13. 	Sub-contracting

# Subcontracting is allowed.

PROVISIONAL TIMETABLE

# 14. 	Provisional commencement date of the contract

19.11.2025

# 15. 	Implementation period of the tasks

16 months

| Activity | Provisional period ((month(s)) of delivery | Delivery after notification by the Contracting Authority |
| --- | --- | --- |
| Lot 1 |  |  |
| A1.1: Development of an integral Marketing strategy with integrated marketing plan | December 2025 – January 2026 | At the start of the contract, the Contractor is considered to be notified for this activity |
| A1.2: Production and post-production of 3 promotional videos | September/October 2026 January/February 2027 | 45 days after request by the Contracting Authority |
| A1.3: Services for establishing and maintenance of social media channels, conducting social media campaign according to the adopted MS, content creation and media publications for the MK side of the CB region | January 2026 – March 2027 | 30 days after request by the Contracting Authority |
| A1.4: Design and printing of promotional materials (Banner flag (1pcs), Notebook (300 pcs), Leaflet (300 pcs), Photoalbum (200 pcs), Roll banner (1pcs), Posters (60pcs), e-banner (10)) | April - July 2026 | 30 days after request by the Contracting Authority |
| Lot 2 |  |  |
| A 2.1: Conducting focus group and interviews | February – March 2026 | 30 days after request by the Contracting Authority |
| A2.2: Preparation of Status report on the readiness for adopting a low-carbon tourism for MK side in the CB region | May – June 2026 | 30 days after request by the Contracting Authority |
| A 2.3: Preparation of Action plan for low-carbon tourism development | November – December 2026 | 30 days after request by the Contracting Authority |
| A 2.4: Preparation of Diary of a cyclist on the Infinity Trail - a cyclist's travelogue. | February – March 2027 | 30 days after request by the Contracting Authority |
| A2.5: Development of Integral velo tour package | April-May 2026 | 30 days after request by the Contracting Authority for the tour piloting |
| A2.6: Tour guide and Velo Guide for piloting the velo tour package | To be determined during contract implementation | 30 days after request by the Contracting Authority |
| A2.7: Development of comprehensive tourist product (joint and cross-border) | November-December 2026 | 30 days after request by the Contracting Authority |

SELECTION AND AWARD CRITERIA

# 16. 	Selection criteria

Capacity-providing entities

An economic operator (i.e. candidate or tenderer) may, where appropriate and for a particular contract, rely on the capacities of other entities, regardless of the legal nature of the links which it has with them. If the economic operator relies on other entities, it must in that case prove to the contracting authority that it will have at its disposal the resources necessary for the performance of the contract by producing a commitment by those entities to place those resources at its disposal. Such entities, for instance the parent company of the economic operator, must respect the same rules of eligibility and notably that of nationality as the economic operator relying on them and must fulfil the selection criteria for which the economic operator relies on them. Furthermore, the data for this third entity for the relevant selection criterion should not be included in the tender form but in a separate document. Proof of the capacity will also have to be provided when requested by the contracting authority.

With regard to technical and professional criteria, an economic operator may only rely on the capacities of other entities where the latter will perform the tasks for which these capacities are required.

With regard to economic and financial criteria, the entities upon whose capacity the economic operator relies, become jointly and severally liable for the performance of the contract.

The following selection criteria will be applied to the tenderers. In the case of tenders submitted by a consortium, these selection criteria will be applied to the consortium as a whole if not specified otherwise. The selection criteria will not be applied to natural persons and single-member companies when they are sub-contractors.

The tenderer shall not use previous experience which caused breach of contract and termination by a contracting authority as a reference for selection criteria. This is also applicable concerning the previous experience of experts required under a fee-based service contract.

#### The selection criteria for each tenderer are as follows

1)	Economic and financial capacity of the tenderer (based on item 3 of the tender form). In case of tenderer being a public body, equivalent information should be provided. The reference period which will be taken into account will be the last three years for which accounts have been closed.

Criterion 1: average annual turnover

The tenderer’s average annual turnover of the last 3 financial years for which the accounts have been closed must be not less than 16400 EUR (for LOT 1)

The tenderer’s average annual turnover of the last 3 financial years for which the accounts have been closed must be not less than 19200 EUR (for LOT 2).

Both lots: In case a tenderer submits an offer for more than one lot, the minimum turnover requirement shall be equal to the sum of the thresholds of the concerned lots.

2)	Professional capacity of the tenderer (based on items 4 and 5 of the tender form). The reference period which will be taken into account will be the last three years preceding the submission deadline.

- Criterion 1: the tenderer has, during the current year and the previous two years, on average, at least one personnel directly employed or otherwise legally contracted on a permanent or non-permanent basis in areas of specialist knowledge related to this contract. (applied separately for each Lot)

- Criterion 2: the tenderer is not subject to professional conflicting interests which may negatively affect contract performance. The presence of professional conflicting interests shall be examined on the basis of the statements made through the Declarations on Honour and, where applicable, the statements and other documents submitted.

3)	Technical capacity of tenderer (based on items 6 of the tender form).

Criterion:

- The candidate has completed services under at least 1 contract implemented at any moment during the last four years before submission deadline.

- For the reference contract, the value of the services completed must be at least 20 % of the estimated value of the lot for which the tender is submitted. Where the tenderer submits an offer for both Lot 1 and Lot 2, the required minimum is 20 % of the combined estimated value of Lot 1 and Lot 2.

- The completed services are in the domain of: tourism development and promotion, including but not limited to developing or upgrading tourism products, delivering specialised training in the tourism sector, providing expert services for the preparation of strategic documents, and carrying out marketing and promotion of tourism products, including content creation for tourism promotion.

This means that the service contract the tenderer refers to could have been implemented at any time during the indicated period but it does not necessarily have to be completed during that period, nor implemented during the entire period. Tenderers are allowed to refer either to service contracts completed within the reference period (although started earlier) or to projects partially implemented during, but not yet completed within the reference period. Only the part completed during the reference period will be taken into consideration. This part will have to be supported by documentary evidence (approval of report or deliverable, proof of payment, statement or certificate from the entity which awarded the contract) also detailing its value. If a tenderer has implemented the project in a consortium, the percentage that the tenderer has successfully completed must be clear from the documentary evidence (approval of report or deliverable, proof of payment, statement or certificate from the entity which awarded the contract) also detailing its value. If a candidate has implemented the project in a consortium, the part that the candidate has successfully completed must be clear from the documentary evidence (such as consortium agreement and bank transfers between consortium members), together with a description of the nature of the services provided.

# 17. 	Award criteria

Best price-quality ratio.

TENDERING

# 18. 	Deadline for submission of tenders

The deadline for submission of tenders is specified in point 8 of the instruction to tenderers.

# 19. 	Tender format and details to be provided

Tenders must be submitted using the standard tender form for simplified procedures, the format and instructions of which must be strictly observed. The tender form is available from the following internet address:

https://wikis.ec.europa.eu/display/ExactExternalWiki/Annexes#Annexes-AnnexesB(Ch.3):Servicecontracts, under the zip file called Simplified Tender dossier.

The tender must be accompanied by a declaration on honour on exclusion and selection criteria using the template available from the following Internet address:

https://wikis.ec.europa.eu/display/ExactExternalWiki/Annexes#Annexes-AnnexesA(Ch.2):General

Any additional documentation (brochure, letter, etc.) sent with a tender will not be taken into consideration.

# 20. 	How tenders may be submitted

Tenders must be submitted in English exclusively to the contracting authority, using the means specified in point 8 of the instructions to tenderers.

Tenders submitted by any other means will not be considered.

By submitting a tender, tenderers accept to receive notification of the outcome of the procedure by electronic means.

# 21.	Alteration or withdrawal of tenders

Tenderers may alter or withdraw their tenders by written notification prior to the deadline for submission of tenders. No tender may be altered after this deadline.

Any such notification of alteration or withdrawal shall be prepared and submitted in accordance with point 9 of the instructions to tenderers.

# 22. 	Operational language

All written communications for this tender procedure and contract must be in English.

# 23.	Additional information

Financial data to be provided by the candidate in the standard application form must be expressed in EUR. If applicable, where a candidate refers to amounts originally expressed in a different currency, the conversion to EUR shall be made in accordance with the InforEuro exchange rate of October/November 2025 which can be found at the following address: http://ec.europa.eu/budget/graphs/inforeuro.html.

* * *

Please note that the EU Official Journal contains the official list of entities subject to restrictive measures and, in case of conflict, it prevails over the list of the EU Sanctions Map.