ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	3

2.2.	Specific objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	4

4.2.	Specific work	4

4.3.	Project management	5

5.	LOGISTICS AND TIMING	5

5.1.	Location	5

5.2.	Start date & period of implementation of tasks	5

6.	REQUIREMENTS	5

6.1.	Personnel	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of North Macedonia

## 1.2    Contracting authority

Association Tourist Union Strumica - Strumica

## 1.3 Country background

The Republic of North Macedonia is characterized by a diverse natural landscape, rich cultural heritage, and a growing interest in alternative forms of tourism. However, the tourism sector—especially in the south-eastern cross-border region remains underdeveloped and unevenly distributed, limiting its contribution to local economies and sustainable growth.

Tourism infrastructure is often lacking or fragmented, and access to key natural and cultural-historical sites remains restricted. Small and medium-sized enterprises (SMEs), which form the backbone of the tourism sector, face difficulties integrating into regional initiatives due to limited capacity and support. Moreover, while the EuroVelo 13 cycling route runs through the region, it remains undeveloped and unmarked on the Macedonian side, missing an opportunity to attract European cycling tourism.

The EU-funded project “Low-Carbon InFinity Trail (LIFT)”, implemented under the Interreg IPA CBC Bulgaria–North Macedonia Programme 2021–2027, addresses these challenges by developing a dedicated cycling trail, upgrading infrastructure, and improving access for people with disabilities. The project promotes sustainable, low-carbon tourism in line with the Green Deal, Territorial Agenda 2030, and national development goals, positioning the region as a competitive and attractive destination within the broader cross-border area.

## 1.4 Current situation in the sector

In North Macedonia, tourism remains an important but underexploited sector with untapped potential, especially in the southeastern regions bordering Bulgaria. The country faces multiple challenges that limit the development of year-round, sustainable tourism, including fragmented infrastructure, poor accessibility to natural and cultural sites, and weak integration of environmentally friendly practices.

Despite growing interest in active and eco-tourism, such as cycling, hiking and rural tourism, many areas lack the basic infrastructure and support services required to meet the expectations of modern tourists. Cycling tourism, in particular, is still in its early stages. Existing cycling trails are often disconnected, unmarked, or in poor condition, and support facilities like rest stops, repair stations, and accessible transport options are largely absent. These gaps prevent the country from fully participating in regional and European cycling networks, such as EuroVelo 13 (Iron Curtain Trail).

Furthermore, marketing and branding of tourism products remain underdeveloped, and there is limited cooperation among tourism stakeholders. Although national strategies promote low-carbon and sustainable development, practical implementation remains slow, particularly at the local level. There is also a need for stronger cross-sector collaboration, better-trained tourism staff, and more inclusive tourism services.

The LIFT project responds to these challenges by introducing an innovative, low-carbon tourism product that builds on North Macedonia’s natural and cultural assets. Through targeted investments in cycling infrastructure, services, and accessibility, the project promotes greener mobility, sustainable tourism development, and stronger cross-border cooperation.

## 1.5 Related programmes and other donor activities

INTERREG VI-A IPA BULGARIA – NORTH MACEDONIA PROGRAMME 2021TC16IPCB006 (2021-2027)

# OBJECTIVES & EXPECTED OUTPUTS

## 2.1 Overall objective

The overall objective (Impact) to which this action contributes is: to unlock the region's tourism potential, drive sustainable economic growth and improve regional competitiveness of the southern BG and MK cross-border region, based on streamline the utilization of the tourism resources and improve tourism marketing and branding practices, through development and test implementation of new approach for low carbon tourism, by developing and upscaling a pilot tourism product "Low-Carbon InFinity Trail" following the newest trends.

## 2.2 Specific objective(s)

The specific objectives (Outcomes) of this contract are as follows:

1) Specific objective (Outcome) 1: To enhance the visibility and public awareness of the project and its cross-border impact by delivering a comprehensive marketing and visibility services for tourism. This includes the development of a strategic marketing plan, targeted social media campaign, production of promotional videos and design and distribution of branded promotional materials. (LOT 1)

2) Specific objective (Outcome) 2: To support the development of sustainable, low-carbon, and experience-based tourism in the cross-border region by providing expert services for analysis, planning, and product development. The services under LOT 2 will deliver an in-depth assessment of tourism readiness, design practical action plans, and create innovative tourism products that integrate cycling, culture, and nature. (LOT 2)

## 2.3 Expected outputs to be achieved by the contractor

The service will be paid on the basis of the delivery of the specified output(s). Payments might be totally or partially withheld if the contractual result(s) have not been reached in conformity with the detailed terms of reference. Payment(s) is/are based on the approval of this/these deliverable(s). Partial payment has to be determined according to the partial implementation of the output(s).

The expected outputs of this contract are as follows:

LOT 1 Marketing and visibility services for tourism

The main outputs which should be achieved through the provision of services under LOT 1 and will contribute to Specific objective (Outcome) 1 are as follows:

Output 1.1: Developed integral Marketing strategy with integrated marketing plan

- Developed Marketing strategy for raising the attractiveness and to promote the CB region as a sustainable and well recognized low-carbon tourist destination.

- Output 1.2: Produced 3 promotional videos

- Created promotional videos highlighting tourist potential of target area, new velo (cycling) tours developed, and encourage stakeholders’ participation in future initiatives.

Output 1.3: Established and maintained social media channels, conducted social media campaign according to the adopted MS, content creation and media publications for the MK side of the CB region

- Established and managed social media accounts on at least two social media platforms and conducted social media campaign based on the developed marketing strategy

Output 1.4: Designed and printed promotional materials

- Banner flag (1pcs), Notebook (300 pcs), Leaflet (300 pcs), Photo album (200 pcs), Roll banner (1pcs), Posters (60pcs), e-banner (10)

LOT 2 Tourism subject matter expert services

The main outputs which should be achieved through the provision of services under LOT 2 and will contribute to Specific objective (Outcome) 2 are as follows:

- Output 2.1: Conducted focus groups and interviews

- Organized a comprehensive focus group and conducted in-depth interviews with representatives from the tourism sector, young people, NGO’s and other relevant stakeholders.

- Output 2.2: Prepared status report

- Prepared status report for MK side of the CB region which provide in-depth assessment of the existing tourism infrastructure, service provisions, cultural and natural sites and cycling related facilities.

- Output 2.3: Prepared action plan

- Prepared detailed action plan for low-carbon tourism development and to increase the attractiveness of the region.

- Output 2.4: Prepared Diary of a cyclist on the Infinity Trail

- Prepared digital cyclist diary that highlights the key experiences, natural wonders, cultural heritage and attractions along the trail.

- Output 2.5: Developed integral Velo tour package

- Developed three (3) velo tour packages combining cultural, historical and natural landmarks as well as local traditions and cuisine.

- Output 2.6: Piloted velo tour package

- Engaged two guides to ensure smooth implementation and safety during the piloting of the developed integral velo tour package.

- Output 2.7: Developed comprehensive tourism (CB) product

- Developed tourism product “Infinity trail” that highlights cultural, natural and historical sites and developed cycling infrastructure.

# ASSUMPTIONS & RISKS

## 3.1 Assumptions underlying the project

Assumptions underlying the project

- Timely communication and continuous provision of information, data and feedback between the Contractor and the Contracting Authority;

- Clear roles and responsibilities by both parties and understanding of the objectives of the contract by the Contractor;

- Timely information for the respective dates of the events provided by the Contracting Authority;

- Regular coordination and assistance by the Contracting Authorities in terms of stakeholder and other parties, and content approvals;

- The contractor has qualified personnel, tools, and knowledge to implement the contract.

## 3.2 Risks

Potential risks to the successful implementation of the contract include:

| Identified risks | Probability | Influence | Risk assessment |
| --- | --- | --- | --- |
| Miscommunication or delays in feedback between contractor and Contracting authority | Low | Substantial | High |
| Insufficient capacity and quality of delivering of services by the contractor | Low | Substantial | High |
| Absence of timely input and feedback from the Contracting Authority on deliverables or recommendations submitted by the contractor during implementation. | Moderate | High | High |
| Delays in the period of start and/or implementation of the contract; | Very low | Moderate | Tolerable |
| Unexpected changes in the subsidy contract which are beyond the authorities of the Contracting Authority. | Low | High | Moderate |

# SCOPE OF THE WORK

## 4.1 General

### Description of the assignment

The scope of this contract covers the provision of services aimed at promoting sustainable tourism and enhancing the visibility of the project “Low-carbon infinity trail” – LIFT which is implementing by the Association Tourist Union Strumica - Strumica (Contracting Authority). It is divided in two separate lots each targeting a specific objective but working in synergy to support the broader goals of regional development and sustainable tourism. Both lots require a high degree of coordination with the contracting authority and relevant local stakeholders to ensure that all outputs are contextually appropriate, effectively implemented, and contribute to the long-term sustainability of tourism development in the CB region. Below is a brief summary of the services to be provided by a potential contractor(s) by lots:

Lot 1 - Marketing and visibility services for tourism

These activities focus on marketing and visibility services for raising public awareness and enhancing the visibility of the project and its impact of the both sides of the cross-border region. Within this scope, the contractor is expected to deliver a comprehensive marketing and visibility package that includes the development of a strategic marketing strategy and marketing plan, establishing social media channels and implementation of a targeted social media campaign, production of promotional videos, and the design and distribution of promotional materials.

The contractor will produce three promotional videos that showcase the tourist potential of the CB region, highlight newly developed cycling tours, and encourage the involvement of stakeholders in future tourism initiatives. A marketing strategy will be prepared in electronic version and will include a detailed marketing plan for social media campaign, direct (offline) promotion etc. It will be base for the establishment and maintenance of two social media channels and for the preparation of the promotional materials.

Lot 2 - Tourism subject matter expert services

This set of activities aims to support the development of sustainable, low-carbon and experience-based tourism in the CB region. This includes services for strategic planning that will enable regional stakeholders to build on existing tourism potential This will involve organizing and conducting focus groups and in-depth interviews with representatives from the tourism sector, youth groups, NGOs, and other relevant stakeholders to gather insights and assess needs. Based on this input, the contractor will prepare a detailed status report for the MK side of the CB region, analyzing current tourism infrastructure, service provision, cultural and natural attractions, and cycling-related facilities. The final component under this lot is the development of a comprehensive action plan that outlines strategic steps for low-carbon tourism development and enhancing the overall attractiveness of the region. The action plan should include actionable recommendations that are realistic, sustainable, and aligned with regional development strategies.

### Geographical area to be covered

Southeast and East regions of Republic of North Macedonia

### Target groups

Target groups are: local and regional public authorities, infrastructure and public service providers, NGOs, SMEs in the field of tourism and general public.

## 4.2 Specific work

The selected contractor(s) within the frame of each LOT need to carry out the tasks and provide the services described below. When preparing their technical proposals, the potential contractor(s) should consider that the task descriptions provided of the tasks is indicative and can serve as a minimum requirement set by the Contracting Authority.

LOT 1: Marketing and visibility services for tourism

The successful implementation of the activities provided in this lot need to result in raised public awareness at the same time enhancing the visibility of the project and its impact. The following specific activities need to be delivered.

Activity 1.1: Development of an integral Marketing strategy with integrated marketing plan

- Objective of the activity & brief description

- The contractor should develop a comprehensive marketing strategy based on cycling and low-carbon concepts aimed at highlight the tourist potential of the cross-border region as a sustainable and well recognized low-carbon tourist destination.

- The objective of the strategy is to highlight the tourist potential in the South-east and East regions in North Macedonia through development of tourism product and creation of recommendations and strategic actions for future actions;

- General information & requirements:

- Strategy timeframe: The marketing strategy and the integrated marketing plan should cover at least a three-year period (2026–2028);

- Language: The document should be developed in English. A translated summary of the strategy, including the key recommendations and strategic actions, must be provided in Macedonian (MK) and Bulgarian (BG).

- Format: The marketing strategy (final document) should be delivered in electronic version (pdf.), comprising approximately 40-60 pages (including text, graphics, photos, annexes etc.).

Documents to be followed: To ensure effective development of the tourism product and implementation of promotional activities, the Contractor must maintain consistent communication with the Contracting Authority. The Contractor should align the structure of the strategy in coordination with the Contracting Authority in order to assure coherence with other project key documents - the Action Plan and Status Report (A2.2 and A2.3 of Lot 2 in this ToR).

- Tasks, responsibilities & specific requirements:

- Documents review and analysis: Conduct a brief analysis of existing project documents, particularly the developed Action Plan and other relevant materials, to ensure alignment with project objectives.

- Desk research and analysis: Perform in-depth desk research to identify target audiences, preferences, and behaviours, and to analyse tourism opportunities and trends in sustainable tourism.

- This research will inform the definition of strategic goals and priorities, the development of a tourism product perspective, and the creation of a comprehensive SWOT analysis.

- Development of visibility toolkit: Creation of draft design for all envisaged promotional materials that will be prepared during the project implementation. The design should be prepared upon request of the Contracting Authority.

- Marketing plan: Detailed plan for online and offline promotion should be prepared. The plan should serve as guidance for the effective implementation of social media campaigns and targeted offline activities, including printed promotional materials and the organization of promotional events.

- Implementation and monitoring: The contractor needs to develop a monitoring tool and checklist to support the implementation process and identify any necessary adjustments.

- This will ensure that the strategy remains flexible and responsive to real-time challenges and outcomes.

- Expected output(s)

- Developed and delivered one (1) comprehensive marketing strategy in accordance with the requirements in English language

- Translated and delivered summary of the strategy, including the key recommendations and strategic actions in MK and BG language;

- Indicative timeframe/period for delivery of the expected output(s): December 2025 - January 2026

- Activity 1.2: Production and post-production of 3 promotional videos

- Objective of the activity & brief description

- The aim of this activity is to increase the attractiveness of the Southeast and East region of North Macedonia by preparing three (3) promotional videos. The contractor needs to develop three (3) promotional videos in order to highlight the tourism potential of the two regions in North Macedonia (east and south-east).

- General information & requirements

- Number of videos: three (3)

- Objective of the videos: To highlight the tourism potential of the East and South-East regions of North Macedonia, with a focus on promoting the regions as attractive, experience-based, and low-carbon tourism destinations.

- Location: Various sites within the South-East and East regions of North Macedonia, in coordination with the Contracting Authority.

- Tasks, responsibilities & specific requirements:

- - Development of concept/scenario - For each video, the contractor should prepare a detailed concept and script. This should include the proposed storyline, key messages, structure of scenes, locations, and visual style.

- *Each concept must be submitted to the Contracting Authority for review, comments, and formal approval prior to the start of filming.

- Filming and footage creation: The contractor should conduct video shooting at selected locations in the East and South-East regions in North Macedonia. This includes planning, coordination of participants (e.g., actors, guides, local stakeholders), capturing both scenic and activity-based footage, and ensuring all essential visuals are covered.

- Post-production and editing: The contractor is responsible for the full editing process, including montage, sound design, color correction, and visual effects (if needed). A draft version of each video should be submitted to the Contracting Authority for review and approval. Feedback must be incorporated into the final version.

- Technical specification:

- - Video duration: 1-2 minutes each video;

- - Quality (minimum resolution): Full HD (1920 x 1080 pixels);

- - Aspect ratio: 16:9; (or other formats, suitable for online promotion and presentation)

- - Music and copyright: Only royalty-free or properly licensed music may be used. The contractor should ensure all intellectual property rights are respected.

- - Visibility rules: The EU visibility and publicity principles, as defined in the Communication and Visibility Manual for EU External Actions, must be followed.

- - Review and approval: Created draft version for each video should be sent to the Contracting Authority for approval. Any comment, additional requirement and recommendation should be respected and implemented.

- *the video footages can be taken in different time periods in previous coordination and communication with the Contracting Authority. The Contracting Authority will inform the Contract for specific event and footage needed at least 10 days before the event.

- Expected output(s)

- Produced and delivered three (3) promotional videos in accordance with the technical specifications and requirements.

- Indicative timeframe/period for delivery of the expected output(s):September/October 2026 for one video and January-March 2027 for the other two videos

- Activity 1.3 Services for establishing and maintenance of social media channels, conducting social media campaign according to the adopted MS, content creation and media publications for the MK side of the CB region

- Objective of the activity & brief description

- The objective of the social media and media campaign is to promote the project’s activities and results, as well as to raise awareness of the importance of the low-carbon tourism in the cross-border area.

- The contractor should establish social media accounts and execute social media & media campaign to raise awareness of the importance of the low-carbon tourism in the cross-border area.

- General information & requirements:

- Documents to be followed: Created Marketing Strategy (with integrated marketing plan) shall be base and guiding framework for implementing successful social media campaign.

- Number of social media channels: 2 (two) social media channels shall be established and managed. Timeframe for social media management / Duration: The Contractor will be notified at least 30 days prior to the commencement of the task. The duration of the social media campaign shall be by the end of the service assignment.

- Tasks, responsibilities & specific requirements:

- Establishment of social media channels. Total of 2 (two) accounts on different social media platforms should be established by the Contractor (e.g. Facebook, Instagram, YouTube, etc.) The exact platforms should be identified in the Marketing Strategy in close communication and coordination with the Contracting Authority.

- Content creation: The contractor is responsible for developing content material for promoting the project activities and results. This includes but not limited to text, photos, infographics, etc. At least 50 social media posts should be published during the entire duration of the service assignment.

- This number of social media posts is for the entire duration of the assignment, while specific timeframes for number of posts to be prepared and published shall be defined in the Marketing Strategy, which will be subject of approval.

- The Contractor should implement the social media campaign in accordance with the approved Marketing Strategy.

- * All content must align with the visibility requirements of the Programme and follow the unified brand identity elements outlined in the Marketing Strategy.

- * A bi-monthly content plan must be submitted for approval by the Contracting Authority in advance.

- Social media management: The Contractor should ensure consistent, timely, and effective management of the established social media channels. This includes: engagement and interactions with the audience/followers, responding to messages and comments, etc. The contractor must follow all instructions and guidelines set out in the Marketing Strategy.

- Local/regional media: The contractor should prepare materials for publication on local/regional electronic media (web banners, PR text, etc.). Total of 3 (three) publications should be prepared. The prepared materials should be submitted for review and approved by the Contracting Authority prior to publication.

- Expected output(s):

- Established social media channels (two) and conducted social media campaign in accordance with the adopted Marketing plan and requirements;

- Created social media content for the entire duration of the social media campaign (with at least 50 posts prepared, delivered and published for the entire duration of the contract assignment)

- Prepared and delivered three (3) PR publications for local/regional electronic media (in forms of PR text, short info, or similar)

- Indicative timeframe/period for delivery of the expected output(s): March 2027

- Activity 1.4 Design and printing of promotional materials

- Objective of the activity & brief description

- The aim of this activity is to design and produce high-quality promotional materials that effectively communicate the results, achievements, and impact of the project to the wider public and key stakeholders. These materials will serve as tools for raising visibility, strengthening outreach, and reinforcing the project’s identity.

All materials must be developed in close communication and coordination with the Contracting Authority and approved prior to printing. All printed materials must follow the EU visibility rules as well as the visibility toolkit defined in the Marketing strategy (Annex Visibility toolkit).

- Technical specifications:

- The following should be designed and printed:

- Banner flag

- Quantity: 1 (one)

- Material: Polyester-based fabric/canvas

- Dimension: 120x80cm

- Color: full color

- Notebook

- Quantity: 300 pieces

- Dimension/format: A6 (minimum)

- Type and material: cover 180-300gsm; Inside-80gsm

- Number of pages: 50 (minimum)

- Color: Cover (color 4+0) Inside (black and white);

- Leaflet

- Quantity: 300 pieces

- Dimension/format: A5 double-sided

- Type and material: Kunstdruk gloss paper (110 – 130 gr/m2)

- Color: full color

- Language: Macedonian and/or English

- Photo album

- Quantity: 200 pieces

- Dimension/format: minimum 21x21cm (or other non-standard format)

- Type and material: Cover (Kondstdruck gloss paper min 220 gr), Inside (Kondstdruck gloss paper min.170 gr);

- Color: (full color 4+4); Inside (0+4)

- Number of pages: 30 pages

- Roll banner

- Quantity: 1 (one) pcs

- Dimension/format: 200x80cm

- Type and material: Vinyl

- Event poster

- Quantity: 60 pieces (5 different designs)

- Dimension/format: A3

- Color: Full color 4+4

- The following should be designed and submitted as electronic format:

- E-banner

- Quantity: 10 pieces

- Dimension/format: 1920x1080

- Aspect ratio: 16:9

- Content: Color design, event and project related

- Expected output(s): Designed, printed and delivered promotional materials specifically as required in this present Terms of Reference.

- Indicative timeframe/period for delivery of the expected output(s): April – July 2026

Lot 2 - Tourism subject matter expert services

Lot 2 focuses on planning and preparing for low-carbon tourism development by engaging stakeholders, assessing current conditions, and designing future actions. The work includes interviews, a status report for the MK region, a detailed action plan, and the creation of new cycling tour experiences like the Infinity Trail and velo packages.

Activity 2.1 Conducting focus group and interviews

- Objective of the activity & brief description: This activity aims to support sustainable tourism development in the cross-border region. Activity 2.1 focuses on organizing a focus group and conducting interviews with stakeholders from the tourism sector, youth, NGOs, and local authorities in North Macedonia. The goal is to gather qualitative insights on current tourism conditions, service gaps, and opportunities for low-carbon improvements along the proposed Low-Carbon Infinity Trail. The findings will contribute directly to the preparation of a Country Status Report and the development of a cross-border Action Plan for low-carbon tourism.

Tasks, responsibilities & specific requirements:

2.1.1. Conducting of Focus group

The Contractor is required to conduct one (1) focus group with a minimum of five (5) participants, consisting of relevant stakeholders from the tourism sector on the MK side.

Participants: representatives of NGOs, tourism service providers, cycling associations, and other related actors.

Type of the focus group: On-site and/or hybrid (Note: The venue will be determined in consultation with the Contracting Authority)

Concept preparation: The Contractor should develop a tailored concept and discussion topics suitable for the target audience.

Themes of the focus group: sustainable tourism development, current challenges and opportunities in the sector, and related issues.

Note*: The Contractor should implement the activity based on the common methodology that will be developed within the project. The common methodology will be provided to the Contractor by the Contracting Authority. The methodology will include general instructions on (but not limited to):

Feedback forms,

Moderating the focus group,

Conducting qualitative analysis of the discussion,

Preparing a brief report summarizing key findings and conclusions.

2.1.2 Conducting Interviews with stakeholders

The Contractor needs to conduct 5 (five) in-depth interviews with relevant stakeholders from the tourism sector.

Potential interviewees: representatives of NGOs, tourism service providers, cycling associations, and other related actors that operate (direct or indirect) in the tourism sector.

Type of interview: face to face or online depending of the availability of the interviewees

Concept preparation: the contractor needs to develop concept and send it to the Contracting Authority for approval.

Note*: The Contractor should implement the activity based on the common methodology that will be developed within the project. The common methodology will be provided to the Contractor by the Contracting Authority.

The methodology will include general instructions on (but not limited to):

Feedback forms,

Moderating the interviews,

Conducting qualitative analysis of the discussion,

Preparing a brief report summarizing key findings and conclusions.

Reporting:

- Preparation of a brief report for the conducted research activities

Upon completion of the focus group and interviews, the contractor needs to prepare brief summary report consolidating key findings, insights and recommendations from both activities. The report will serve as a foundational document for the implementation of subsequent activities within this lot, such as Status report and preparation of Action plan. The structure of the report will be established within the common methodology which shall be provided by the Contracting Authority to the Contractor.

- Expected output(s):

- Delivered one (1) report the on key findings, insights and recommendations from the conducted research activities.

- Indicative timeframe/period for delivery of the expected output: Febuary – March 2026

Activity 2.2 Preparation of Status report on the readiness for adopting a low-carbon tourism for MK side in the CB region

Objective of the activity & brief description: This activity aims to support sustainable tourism development in the cross-border region. Activity 2.2 includes the preparation of a Status Report for the Macedonian side of the CB region. The objective is to provide an in-depth and evidence-based assessment of the existing tourism infrastructure, service offerings, cultural and natural attractions, and cycling-related facilities. This report will serve as a key input for the development of a joint cross-border Status Report and Action Plan for low-carbon tourism. The national status report will be based on the findings from the previously conducted focus group discussions and stakeholder interviews (Activity 2.1), complemented by additional data collection through desk research, online tools, and surveys.

- General information & requirements:

The report should include at least the following elements (not limited to):

- Overview of the current tourism infrastructure and services

- Mapping of cultural, natural and cycling-related assets

- Identified challenges, opportunities and recommendations for low-carbon tourism development

- Insert different visuals such as charts, maps, tables where applicable to support data presentation

This report will serve as a foundational document for the preparation of the joint cross-border status report.

Indicative number of pages: The Contractor should prepare the Status report with a total length of minimum 20 to maximum 35 pages, excluding annexes. The report should be concise yet comprehensive, incorporating relevant visuals (e.g., charts, tables, and maps) to support the findings.

Language: The report should be prepared on Macedonian language

Tasks, responsibilities & specific requirements:

Data analysis: The contractor should review the report from the conducted interviews and focus group in order to identify which information and data have already been collected and determine what additional topics or areas require further research.

Data collection: The contractor should collect additional relevant data using desk research (using available statistical data, relevant reports, studies, and other sources) & surveys (to gather insights from relevant stakeholders not previously engaged in Activity 2.1) The aim of the research is to gain a comprehensive understanding of the current state of tourism in the MK side of the cross-border region, the perspectives on low carbon tourism and to identify areas for improvement and innovation. The main geographic focus will be on the Municipality of Strumica and Municipality of Berovo, along with other relevant municipalities or surrounding areas that are important for the successful implementation of the activity.

- Expected output(s):

- Prepared and delivered one (1) national status report in Macedonian language. The contractor should develop a comprehensive and analytical status report for the MK side of the CB region. The report must synthesize data and findings from the previous activity (Acitivity 2.1) and the conducted data collection within this activity.

Indicative timeframe/period for delivery of the expected output: May-June 2026

Activity 2.3 Preparation of Action plan for low-carbon tourism development

- Objective of the activity & brief description:

- The aim of this activity is to develop a detailed Action Plan for the CB region that will serve as a strategic framework for creating an attractive, multidimensional, and all-season tourism product. The Action Plan will be grounded in the principles of low-carbon tourism and will promote the use of newly developed infrastructure, as well as the existing sustainable tourism offer in the region. It will also encourage cross-border cooperation, benefit the local economy, and contribute to environmental protection. The objective of the Action plan is to promote the use of newly developed infrastructure, as well as the existing sustainable tourism offer in the region.

- General information & requirements:

The Action plan should include at least the following elements (not limited to):

- - Identification of areas for improvement and investment,

- - Allignment with low-carbon principles and current tourism trends,

- - Propose activities that benefit the environment, local communities, businesses, and tourists

- - Monitoring and evaluation (M&E) checklist: The Contractor should develop a checklist for monitoring and evaluation of the Action Plan’s implementation, including:

- Key performance indicators (KPIs),

- Baselines and targets,

- Monitoring tools/methods, and

- Timeline for evaluation.

- The document should be evidence-based and actionable, with short-, medium-, and long-term measures.

- Indicative number of pages: Minimum 25 pages

- Language: The full Action Plan should be developed in English language. Short summary of the Action Plan shall be translated in Macedonian and Bulgarian.

Tasks, responsibilities & specific requirements:

- Review and analysis: The Contractor should review and analyze the overall cross-border Status Report and the input collected through a series of small-scale consultation events held in the target municipalities in Bulgaria. This input shall be provided by the Contracting Authority.

- This analysis will help consolidate existing findings and identify key thematic areas for strategic planning.

- Complementary research and stakeholder consultations: The Contractor should conduct additional research and consultations with relevant stakeholders in both countries, aimed at enriching the Action Plan with up-to-date, diverse, and context-specific perspectives. This task builds on the in-depth research previously conducted and helps ensure that the plan reflects local needs and opportunities.

- Expected output(s):

- Prepared and delivered one (1) Action Plan report in English language.

- Translated summary of the Action Plan (key findings, priorities, and measures) in Macedonian and Bulgarian language .

- Indicative timeframe/period for delivery of the expected output: November-December 2026 (The Contractor will be notified at least 30 days prior to the commencement of the task i.e. after the completion of the other documents/activities which will serve as base for the preparation of the Action Plan)

Activity 2.4 Preparation of Diary of cyclist on the Infinity Trail - a cyclist's travelogue.

Objective of the activity & brief description: This activity involves the development of a digital travel diary titled “Diary of a Cyclist on the Infinity Trail,” which will serve as an engaging and informative resource for cyclists exploring the newly developed low-carbon tourist route known as the Infinity Trail. The diary will highlight key experiences, natural wonders, cultural heritage, and attractions along the trail, offering users a unique narrative-based insight into the route. The objective of this activity is to to create a visually appealing, engaging, and informative digital cyclist diary that promotes the Infinity Trail as a compelling low-carbon tourism product, while enhancing the visibility and appeal of the trail to local and international visitors.

- General information & requirements:

Format: PDF (or other applicable) format. The document shall be delivered in a format applicable for integration on the web-portal and web application of the Infinity trail

Number of pages: 20-30 pages

Language: The diary should be prepared and delivered by the Contractor in English language. Following the approval of the diary, the Contractor shall translate and deliver the integral Diary in Macedonian language and in Bulgarian language.

Tasks, responsibilities & specific requirements:

Content creation: The Contractor should develop original content for the Diary such as:

- Narrative-style stories and reflections that follow the cycling experience on the Infinity trail. The Contractor should develop the content as if told by the cyclist (description of the day’s route, personal impressions, unique sights along the path, etc.)

- Captivating phots of the trail, surroundings, attractions and cyclist experiences

- Illustrative materials such as maps, route highlights, etc.

Design and layout: The Contractor should design the Diary using a user-friendly, modern and visual attractive layout suitable for web and mobile presentation. The design should align with the EU visibility routes and the visual elements of the project

Integration of content: The contractor should integrate the written and visual content into a unified format and ensure the travelogue is ready for digital publishing. It should be send to the Contracting Authority for review and approval.

Expected output(s):

- Prepared and delivered one (1) Diary of cyclist on the Infinity Trail - a cyclist's travelogue in English language.

- Translated and delivered versions of the Diary in Macedonian language and in Bulgarian language.

Indicative timeframe/period for delivery of the expected output: February-March 2027

Activity 2.5 Development of Integral velo tour package

Objective of the activity & brief description: The objective of this activity is to develop unique velo tour package aimed at promoting sustainable tourism in the cross-border region. The package shall combine cycling with other forms of alternative tourism, such as exploration of cultural, historical, and natural landmarks, as well as local traditions and cuisine.

The Contractor needs to develop three (3) different tour packages which will later be piloted.

- General information & requirements:

Number of velo tour packages: The contractor should develop three (3) different velo tour packages

Location: Various sites/locations in the East and South-east part of North Macedonia

Format: The Contractor needs to submit the developed tour packages in electronic version (pdf format) to the Contracting Authority for approval.

Number of pages per tour: 5-10 pages

Language: The velo tour packages should be prepared in Macedonian language

Tasks, responsibilities & specific requirements:

Design of velo tour packages: The Contractor should develop three (3) different velo tour packages which will be piloted in the South-east and East region in the North Macedonia. Each tour should include cycling activities (including the newly constructed cycle trail under the project) and incorporate at least three (3) different additional experience such as visiting significant historical/natural landmarks, traditional cuisine tastings, visiting crafts workshops and other engaging local activities that contribute to creating a memorable and unique experience for tourists/participants.

Establishing creative names: Creative and unique name/title to be given for each tour. The name should be short, catchy and name that reflects the theme and essence of the specific tour.

Draft agenda: Draft program/agenda should be prepared for each velo tour outlining the starting point, time allocation for each activity, cycling duration and cycling route.

Promotional text: For each tour, a short promotional text must be prepared, including key information and descriptions of each site to be visited (e.g., historical landmarks, craft workshops, culinary stops, sports-related experiences, etc.). The text should be accompanied by photos, charts/tables, and other visual or creative elements suitable for promotional purposes on online platforms.

Submission: The complete velo tour packages – including all texts, photographs, and draft agendas – must be submitted to the Contracting Authority for review, feedback, and final approval.

Expected output:

- Prepared, designed and delivered one (1) integral velo tour package (with three different tours included, in PDF format, in Macedonian language)

Indicative timeframe/period for delivery of the expected output: April-May 2026

Activity 2.6 Tour guide and velo guide for piloting of the velo tour package

Objective of the activity & brief description: The objective of this activity is to pilot the tours which have been developed as part of the integral velo tour package (A2.5). The engagement of tour guide and velo guide shall ensure smooth implementation and participant safety during the piloting of the velo tours.

- General information & requirements:

Objective: The activity aims to enhance the overall experience of participants through guided interpretation and on-site support.

Number of guides: 2 (two). The contractor should engage one tour guide and one velo guide for piloting of the velo tours

Number of tours: 3 (three). All three tours which are part of the integral velo package shall be piloted

Location: Various sites across East and South-east region in North Macedonia as defined in the developed velo tour packages

Reports: After completion of the piloting of the velo tour package the Contractor shall deliver one short report.

Tasks, responsibilities & specific requirements:

Tour guide: Tour guide that will be responsible for the implementation and facilitation of the tours which are part of the velo tour package (from the start till the end). The guide needs to ensure:

-   Following the planned agenda and schedule

- Providing relevant information and interpretation about visited sites (cultural, historical, and natural),

- Facilitating group dynamics and engaging participants in the planned activities and

- Acting as the primary point of contact for participants during the tour.

Velo guide: The velo guide will be responsible for the safe and effective management of the cycling component of the tour. Responsibilities include:

- Leading the cycling group along the designated route

- Ensuring group safety by providing guidance on cycling behavior and route conditions

- Offering basic technical support and assistance in case of mechanical issues or participant difficulties.

- Monitoring the pace and condition of participants to ensure a safe and enjoyable experience.

Both guides should ensure smooth implementation and participant safety during the piloting of the velo tour package.

Expected output:

- Piloted integral velo tour package (with 3 tours included) with engagement of one (1) tour guide and one (1) velo guide.

Indicative timeframe/period for delivery of the expected output: Considering that this is an outdoor activity, the piloting of the velo tour package shall be completed in coordination with the Contracting Authority, depending on weather conditions and availability.

Activity 2.7 Development of comprehensive tourist product

Objective of the activity & brief description: To develop a comprehensive and visually appealing tourism product “Infinity trail” showcasing cultural, natural, historical, and thematic attractions along the LIFT trail, in alignment with sustainable and low-carbon tourism practices.

- General information & requirements:

Objective: Create a cross-border tourism product highlighting the region’s potential and the newly developed cycling infrastructure.

Development of tourist product: A full package consisting of descriptive text, visual elements, maps, tables/charts and branding components.

Format: The document should be send to the Contracting Authority in electronic format (pdf).

Language:

- Communication messages and descriptions: prepared in English and translated into Macedonian and Bulgarian.

- Promotional elements (name and slogan): developed in English and translated into Macedonian and Bulgarian, only if applicable.

Tasks, responsibilities & specific requirements:

Basis documents: The tourist product shall be developed in accordance with the developed Action Plan and the Marketing Strategy.

Description of tourist product: The contractor should create a product that strickly highlights the tourist potential in the regions from the cross-border of Bulgaria and North Macedonia. This should be product that covers the following: summary of relevant project results related to tourism, overview and description of key tourist attractions (cultural, natural, historic), Connection to the newly developed infrastructure (e.g., cycling routes)

- Brand identity of the product

- Creative name and key messages: The contractor should propose a creative, relevant, and memorable name for the tourism product, suitable for a cross-border region and in line with cycling and alternative tourism themes. The name shall be aligned with the concept of “Infinity Trail”, which serves as the basis and overarching idea of the product.

- Key communication messages should also be developed to support the product's visibility and appeal.

Logo: After the tourist product description is approved, the contractor should design a logo reflecting the identity, values, and experience offered by the “Infinity Trail.” The logo should be visually adaptable for print and digital use and submitted for approval in both editable and final formats.

Slogan: powerful, concise, and appealing slogan should be developed to inspire visitors to explore the cross-border area between Bulgaria and North Macedonia.

- Description of tourist elements and trails: The contractor should provide descriptions of all tourism elements integrated in the product, including: trail routes and key waypoints, cultural and natural sites of interest, activities and experiences (e.g., cycling, gastronomy, traditional crafts, heritage sites), suggestions for thematic tours and packages (e.g., eco-tourism, adventure, rural experiences).

Expected output: Prepared and delivered one (1) comprehensive tourism product in electronic format (PDF), including descriptive texts, branding components (name, logo, slogan, key messages), and visual elements (maps, tables, charts).

Indicative timeframe/period for delivery of the expected output: November-December 2026

## Project management

### 4.3.1 Responsible body

Association Tourist Union Strumica - Strumica in its capacity of a project partner in project “Low-carbon infinity trail” (Acronym: LIFT) is the responsible Contracting Authority.

### Management structure

The Association Tourist Union Strumica – Strumica is the Contracting Authority and is responsible for the overall implementation and coordination of the project. It will lead the tendering process and ensure the smooth execution of all related tasks, including contracting external service providers, overseeing the quality and progress of the work, authorizing payments, and managing the project on a day-to-day basis.

The project implementation team within the Association Tourist Union includes a Communication and Visibility Officer and an Accountant, who will handle operational and communication aspects of the project. The legal representative of the Association is designated as the authorized person for signing contracts and approving payments.

### Facilities to be provided by the contracting authority and/or other parties

No facilities to be provided

# LOGISTICS AND TIMING

## 5.1 Location

The location for implementing the envisaged activities and tasks within this tender procedure must be within the eligible area of the Cross Border region of Bulgaria and North Macedonia.

The piloting of the velo tour package shall focus on the South-east and East region of North Macedonia.

## 5.2 Start date & period of implementation of tasks

The intended start date is 19.11.2025 and the period of implementation of the contract will be 16 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## 6.1 Personnel

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, should only be able to provide input as experts if well justified. The justification should be submitted with the tender and should include information on the added value the expert will bring as well on any potential interference or conflict of interest of the proposed expert in his/her function as expert and his/her present or previous functions working as civil servant. Moreover proof should be submitted that the expert is seconded or on personal leave.

The selection procedures used by the contractor to select the experts who provide input to the contract must be transparent, must guarantee the absence of professional conflicting interests and the absence of any discrimination based on former or current nationality, gender, place of residence, or any other ground. The findings of the selection panel must be recorded.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Experts

Minimum requirements for experts are not defined

### Support facilities & backstopping

The costs for support facilities, including backstopping, are included in the tenderer's financial offer.

## 6.2 Office accommodation

Office accommodation for each expert providing input to the contract is to be provided by the contractor.

## 6.3 Facilities to be provided by the contractor

The contractor should ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## 6.4 Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## 7.1 Reporting requirements

The contractor will submit the following reports in English in one original

- Inception Report of maximum 12 pages to be produced after 15 (fifteen) days from the start of implementation. In the report the contractor should describe e.g. initial findings, progress in collecting data, any difficulties encountered or expected in addition to the work programme and staff travel. The contractor should proceed with his/her work unless the contracting authority sends comments on the inception report.

- Interim report in a free format including relevant annexes - submitted not later than 10 working days after completion of half of the contract duration (see 4.2 of this ToR) accompanied by a full delivery - acceptance sheet of the provided services in the respective period. The approval of the report will be a prerequisite for completing the interim payment of the contract. Note: The Contractor is not obliged to deliver an Interim report and in that case, no interim payment will be executed.

Draft final report of maximum 10 pages (main text, excluding annexes) in free format. This report should be submitted no later than one month before the end of the period of implementation of tasks.

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 7 working days after receipt of comments on the draft final report. The report should contain a sufficiently detailed description of the different options to support an informed decision on approval of the report. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

- Other relevant information for the reports: The reports need to be delivered for Lot 1 and Lot 2 separately and independently.

## 7.2 Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

In the absence of comments or approval by the Contracting Authority within 7 to 10 working days (depending on the complexity) the reports are deemed to be approved

- Note: The contractor should deliver the reports either in hard copy on the address given in this tender dossier or electronically by e-mail.

# MONITORING AND EVALUATION

## 8.1 Definition of indicators

## LOT 1: SERVICES FOR STRATEGY DEVELOPMENT FOR ALTERNATIVE TOURISM AND PROMOTION

| ## Activity | ## Output indicator | ## Sources for verification (indicative) |
| --- | --- | --- |
| Activity 1.1 Development of an integral Marketing strategy with integrated marketing plan | ## One comprehensive marketing strategy with integrated three-year marketing plan developed, highlighting the tourism potential of the South-East and East regions of North Macedonia | - Final version of Strategy (PDF format) in English language with additional annexes ## Translated summary in Macedonian and Bulgarian |
| ## Activity 1.2 Production and post-production of 3 promotional videos | ## Three (3) promotional videos produced and finalized, promoting the tourism potential of the East and South-East regions of North Macedonia, in line with the approved concept and technical specifications. | - Approved video concepts and scripts - Draft and final versions of the three videos - Photos from filming locations/events - Media links or reports showing publication/use of the videos (e.g., YouTube, social media, websites) - Delivery report or confirmation of delivery from the contractor |
| ## Activity 1.3 Services for establishing and maintenance of social media channels, conducting social media campaign according to the adopted MS, content creation and media publications for the MK side of the CB region | ## Two social media channels established and actively managed, with at least 50 content posts published, and three media publications prepared and disseminated, in line with the approved Marketing Strategy and EU visibility requirements. | - Links/screenshot of the created social media channels - Links/screenshot of the published posts - Approved bi-monthly content plans - Links/Screenshot of media publications |
| - Activity 1.4: Design and printing of promotional materials | Prepared design and printed following materials: Banner flag Notebook Leaflet Photo album Roll banner Event poster Prepared design and published: ## E-banner | - Delivery acceptance sheet for the prepared promotional materials - Screenshot of e-banner |

LOT 2: TOURISM SUBJECT MATTER EXPERT SERVICES

| Activity | Output indicator | Sources for verification (indicative) |
| --- | --- | --- |
| Activity 2.1 Conducting focus group and interviews | One (1) focus group organized and conducted with a minimum of five participants, five (5) in-depth interviews completed with key tourism stakeholders, and a consolidated summary report prepared outlining key findings, insights, and recommendations for future low-carbon tourism planning. | - List of participants - Photos - Audio recording and/or transcript |
| Activity 2.2 Preparation of Status report | One national status report developed for the MK side of the cross-border region | Final version of Status report (in Macedonian language) |
| Activity 2.3 Preparation of Action plan | One (1) cross-border Action Plan developed, providing a strategic framework for low-carbon tourism development in the CB region between North Macedonia and Bulgaria | - Final version of the Action Plan (in English) Translated summary of the Action Plan in Macedonian and Bulgarian |
| Activity 2.4 Preparation of Diary of cyclist on the Infinity Trail - a cyclist's travelogue | One digital “Diary of a Cyclist on the Infinity Trail” created, designed, and formatted for web and mobile presentation | - Final version of the digital diary in English (PDF format) Translated versions in Macedonian and Bulgarian |
| Activity 2.5 Development of Integral velo tour package | One (1) integral velo tour package developed in Macedonian language | - Final version of the velo tour package (pdf format) |
| Activity 2.6 Tour guide and velo guide for piloting of the velo tours | One (1) integral velo tour package piloted with the engagement of one (1) tour guide and one (1) velo guide | - Photos of the piloting - Agenda - Short piloting report |
| Activity 2.7 Development of comprehensive tourist product | One (1) comprehensive cross-border tourism product “Infinity Trail” developed, integrating cultural, natural, and historical sites with cycling infrastructure. | - Final version of the tourism with all required elements |

REPORTING – Lot 1

| Type of report | Output indicator | Sources for verification (indicative) |
| --- | --- | --- |
| Inception report | Prepared and delivered Inception report according to the requirements given in 7.1 | - Availability of the report in hard copy and/or electronic version |
| Interim report | Prepared and delivered Interim report according to the requirements given in 7.1 | - Availability of the report in hard copy and/or electronic version |
| Final report | Prepared and delivered Final report according to the requirements given in 7.1 | - Availability of the report in hard copy and/or electronic version |

REPORTING – Lot 2

| Type of report | Output indicator | Sources for verification (indicative) |
| --- | --- | --- |
| Inception report | Prepared and delivered Inception report according to the requirements given in 7.1 | - Availability of the report in hard copy and/or electronic version |
| Interim report | Prepared and delivered Interim report according to the requirements given in 7.1 | - Availability of the report in hard copy and/or electronic version |
| Final report | Prepared and delivered Final report according to the requirements given in 7.1 | - Availability of the report in hard copy and/or electronic version |

## 8.2 Special requirements

n/a

* * *